## info
matricola | nome | cognome | istruzioni |  |  | caselle input project manager
0512115427 | Antonio | Albanese |  |  |  | caselle input team
0512115910 | Francesco Pio | Contaldo |  |  |  | dati non modificabili
0512106454 | Crystian | Esposito |  |  |  | titoli non modificabili
0512108680 | Iliano | Fasolino
0512114908 | Marco | Greco
0512114332 | Giuseppe Pio | Sorrentino |  | inserire valori solo nelle caselle di input
|  |  |  | password per sbloccare la protezione : U2FsdGVkX1+FH1bXLZKO86mlvJsM4IkH25YXXZkxCpM5Te9DF5OIGoQMMcKqAfpz |  | U2FsdGVkX19QkHVqrDYWimh3WO0goLvn6wvXZlep8785saQ5bAfacYdsdjlRP/uW
PASSWORD
|  |  |  | PMs | U2FsdGVkX19BsJ7RzCPrO9wFHSav2fDIeYJ0LHHT8jg=
|  |  |  | Antonio Albanese | U2FsdGVkX1+bXv8eIBO5/hREGsKGv31XB1hdjE9PRyQ=
|  |  |  | Francesco Pio Contaldo | U2FsdGVkX1+7KSXjXPj9YWv92nC8HzBNIc/8iDu31js=
|  |  |  | Cristyan Esposito | U2FsdGVkX1+U+yb/QgckxT8W7/TIrhoodrIutDp9rPA=
|  |  |  | Iliano Fasolino | U2FsdGVkX18WwbSnO7XFhqel7JNLvCMtdbpQWCyMWiU=
|  |  |  | Marco Greco | U2FsdGVkX18HD/rx4ylPc3czIbgHeTABI+oP9BiEx4U=
|  |  |  | Giuseppe Pio Sorrentino | U2FsdGVkX1/wVwMkAPjuqO/FXiMO5RrINhGXxqhlQvs=

## riassuntoTotale
| Albanese | Contaldo | Esposito | Fasolino | Greco | Sorrentino
2023-10-16 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
2023-10-17 | 0 | 0 | 0 | 0 | 0 | 0
2023-10-18 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0
2023-10-19 | 0 | 0.5 | 0 | 0.5 | 0 | 0
2023-10-20 | 0 | 0 | 0.5 | 0 | 0 | 0
2023-10-21 | 0 | 0 | 0 | 0 | 0 | 0
2023-10-22 | 0 | 0 | 0 | 0 | 0 | 0
2023-10-23 | 1.5 | 1.5 | 0 | 1.5 | 1.5 | 1.5
2023-10-24 | 0.34 | 0.5 | 0 | 0.5 | 0.34 | 0.34
2023-10-25 | 0 | 0.25 | 0.34 | 0.25 | 0 | 0
2023-10-26 | 0 | 0.34 | 0 | 0.34 | 0 | 0
2023-10-27 | 0 | 0 | 0 | 0 | 0 | 0
2023-10-28 | 0 | 0 | 0 | 0 | 0 | 0
2023-10-29 | 0 | 0 | 0 | 0 | 0 | 0
2023-10-30 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
2023-10-31 | 0 | 1 | 0 | 1 | 0 | 0
2023-11-01 | 0.5 | 0 | 0 | 0.17 | 0.5 | 1
2023-11-02 | 0.17 | 0.17 | 0 | 0 | 0.17 | 0.17
2023-11-03 | 0 | 0 | 0 | 0 | 0 | 0
2023-11-04 | 0 | 0 | 0 | 0 | 0 | 0
2023-11-05 | 0 | 0 | 0.17 | 0 | 0 | 0
2023-11-06 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
2023-11-07 | 1 | 0.5 | 0 | 0.5 | 1.25 | 1.25
2023-11-08 | 0.25 | 0.5 | 0.75 | 0.75 | 0.25 | 0.25
2023-11-09 | 0.09 | 0 | 0.25 | 0.5 | 0.25 | 0.25
2023-11-10 | 0.25 | 0.5 | 0.67 | 0.5 | 0.25 | 0.15
2023-11-11 | 0.25 | 0.5 | 0.41 | 0.25 | 0 | 0
2023-11-12 | 0 | 0.17 | 0.41 | 0.1 | 0 | 0
2023-11-13 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
2023-11-14 | 0.25 | 0.15 | 0.51 | 0.15 | 0.5 | 0.25
2023-11-15 | 0.5 | 0.1 | 0 | 0.1 | 0.25 | 0.25
2023-11-16 | 0.25 | 0.5 | 0.17 | 0.5 | 0.25 | 0.15
2023-11-17 | 0.5 | 0.5 | 0.17 | 0 | 0 | 0.5
2023-11-18 | 0 | 0 | 0.17 | 0.5 | 0.25 | 0.25
2023-11-19 | 0 | 0.5 | 0.5 | 0.15 | 0.5 | 0
2023-11-20 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
2023-11-21 | 0 | 0.25 | 0.25 | 0.25 | 0.25 | 0.5
2023-11-22 | 0.25 | 1 | 0.25 | 0.5 | 0.75 | 1
2023-11-23 | 0.5 | 1 | 0.5 | 1 | 0 | 0
2023-11-24 | 0.25 | 0.75 | 0.5 | 0 | 0.5 | 0.5
2023-11-25 | 0 | 0.25 | 0.33 | 0.9 | 0.25 | 1
2023-11-26 | 0 | 1 | 0.75 | 1.8 | 0.5 | 0.76
2023-11-27 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
2023-11-28 | 0.25 | 1.5 | 1.5 | 0 | 0.25 | 0
2023-11-29 | 0 | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-30 | 0.25 | 0 | 0.33 | 0.25 | 0 | 0
2023-12-01 | 0.5 | 0.74 | 0.21 | 0 | 0.5 | 0
2023-12-02 | 0.25 | 1.5 | 1.5 | 0.5 | 0 | 1
2023-12-03 | 0 | 0 | 0 | 0 | 0 | 0
2023-12-04 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
2023-12-05 | 0.5 | 0 | 0 | 0.5 | 0 | 0.5
2023-12-06 | 0 | 0.66 | 0.66 | 1 | 1 | 1
2023-12-07 | 0.5 | 0 | 0.33 | 1 | 0 | 0.5
2023-12-08 | 0 | 0.33 | 0 | 0 | 0 | 0
2023-12-09 | 0 | 0 | 0 | 0 | 0 | 0
2023-12-10 | 0 | 0 | 0 | 0 | 1 | 0
2023-12-11 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
2023-12-12 | 0 | 0 | 0 | 0 | 0 | 0
2023-12-13 | 0 | 0 | 0 | 0 | 0 | 0
2023-12-14 | 0 | 0 | 0 | 0 | 0 | 0
2023-12-15 | 0 | 0 | 0 | 0 | 0 | 0
2023-12-16 | 0 | 0 | 0 | 0 | 0 | 0
2023-12-17 | 0 | 0 | 0 | 0 | 0 | 0
2023-12-18 | 0 | 0 | 0 | 0 | 0 | 0
2023-12-19 | 1.16 | 1.16 | 4.51 | 1.31 | 2.16 | 1.16
2023-12-20 | 1 | 0.5 | 0 | 0 | 2.5 | 0
2023-12-21 | 0 | 2.5 | 2 | 2.5 | 3 | 0
2023-12-22 | 0.5 | 3 | 3.99 | 3 | 1 | 1.5
2023-12-23 | 2 | 3 | 0 | 4 | 3 | 2
2023-12-24 | 3 | 1.75 | 0 | 2 | 2 | 2
2023-12-25 | 0 | 3 | 0 | 2 | 0 | 2
2023-12-26 | 4 | 2.75 | 0 | 2 | 0 | 3
2023-12-27 | 4 | 2 | 0 | 3 | 4 | 2
2023-12-28 | 3 | 2 | 1.08 | 1.65 | 2 | 2.5
2023-12-29 | 3 | 2 | 2.41 | 1.2 | 2 | 3
2023-12-30 | 0.5 | 1 | 0 | 1 | 0.5 | 0
2023-12-31 | 0 | 1 | 0 | 0 | 0 | 0
2024-01-01 | 0 | 1 | 0 | 0 | 0 | 0
2024-01-02 | 1.5 | 1 | 2 | 0 | 0 | 0
2024-01-03 | 2 | 1 | 1.5 | 0 | 0 | 2
2024-01-04 | 0 | 1 | 3.5 | 0 | 2 | 0
2024-01-05 | 0 | 1 | 1.5 | 0 | 0 | 0
2024-01-06 | 0 | 0 | 0 | 0 | 0 | 0
2024-01-07 | 0 | 1 | 0 | 0.88 | 2 | 0.5
2024-01-08 | 0.5 | 0.5 | 0.58 | 0 | 1 | 2
2024-01-09 | 0.5 | 0.5 | 2.16 | 0.75 | 1 | 0.5
2024-01-10 | 0 | 0 | 0 | 0 | 0 | 0
2024-01-11 | 1 | 0 | 0 | 0 | 1.15 | 1.65
2024-01-12 | 0.5 | 0 | 0 | 0 | 1 | 1.5
2024-01-13 | 0 | 0 | 0 | 0 | 0 | 0
2024-01-14 | 0 | 0 | 0 | 0 | 0 | 0
2024-01-15 | 0 | 0 | 0 | 0 | 0.5 | 0
2024-01-16 | 0.5 | 1 | 1.5 | 1 | 0.5 | 2
2024-01-17 | 0 | 0 | 6.5 | 8.5 | 0 | 0
2024-01-18 | 0 | 0 | 0 | 0 | 0 | 0

## statisticheTotale
Pagina satistiche
id | numero ore lavoro
0512115427 | 49.76
0512115910 | 63.57
0512106454 | 57.86
0512108680 | 63.5
0512114908 | 54.57
0512114332 | 54.63
ore lavoro totali
343.89

## riassuntoInBudget
| Albanese | Contaldo | Esposito | Fasolino | Greco | Sorrentino
2023-10-16 | 0 | 0 | 0 | 0 | 0 | 0
2023-10-17 | 0 | 0 | 0 | 0 | 0 | 0
2023-10-18 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0
2023-10-19 | 0 | 0.5 | 0 | 0.5 | 0 | 0
2023-10-20 | 0 | 0 | 0.5 | 0 | 0 | 0
2023-10-21 | 0 | 0 | 0 | 0 | 0 | 0
2023-10-22 | 0 | 0 | 0 | 0 | 0 | 0
2023-10-23 | 0 | 0 | 0 | 0 | 0 | 0
2023-10-24 | 0.34 | 0.5 | 0 | 0.5 | 0.34 | 0.34
2023-10-25 | 0 | 0.25 | 0.34 | 0.25 | 0 | 0
2023-10-26 | 0 | 0.34 | 0 | 0.34 | 0 | 0
2023-10-27 | 0 | 0 | 0 | 0 | 0 | 0
2023-10-28 | 0 | 0 | 0 | 0 | 0 | 0
2023-10-29 | 0 | 0 | 0 | 0 | 0 | 0
2023-10-30 | 0 | 0 | 0 | 0 | 0 | 0
2023-10-31 | 0 | 1 | 0 | 1 | 0 | 0
2023-11-01 | 0.5 | 0 | 0 | 0.17 | 0.5 | 1
2023-11-02 | 0.17 | 0.17 | 0 | 0 | 0.17 | 0.17
2023-11-03 | 0 | 0 | 0 | 0 | 0 | 0
2023-11-04 | 0 | 0 | 0 | 0 | 0 | 0
2023-11-05 | 0 | 0 | 0.17 | 0 | 0 | 0
2023-11-06 | 0 | 0 | 0 | 0 | 0 | 0
2023-11-07 | 1 | 0.5 | 0 | 0.5 | 1.25 | 1.25
2023-11-08 | 0.25 | 0.5 | 0.75 | 0.75 | 0.25 | 0.25
2023-11-09 | 0.09 | 0 | 0.25 | 0.5 | 0.25 | 0.25
2023-11-10 | 0.25 | 0.5 | 0.67 | 0.5 | 0.25 | 0.15
2023-11-11 | 0.25 | 0.5 | 0.41 | 0.25 | 0 | 0
2023-11-12 | 0 | 0.17 | 0.41 | 0.1 | 0 | 0
2023-11-13 | 0 | 0 | 0 | 0 | 0 | 0
2023-11-14 | 0.25 | 0.15 | 0.51 | 0.15 | 0.5 | 0.25
2023-11-15 | 0.5 | 0.1 | 0 | 0.1 | 0.25 | 0.25
2023-11-16 | 0.25 | 0.5 | 0.17 | 0.5 | 0.25 | 0.15
2023-11-17 | 0.5 | 0.5 | 0.17 | 0 | 0 | 0.5
2023-11-18 | 0 | 0 | 0.17 | 0.5 | 0.25 | 0.25
2023-11-19 | 0 | 0.5 | 0.5 | 0.15 | 0.5 | 0
2023-11-20 | 0 | 0 | 0 | 0 | 0 | 0
2023-11-21 | 0 | 0.25 | 0.25 | 0.25 | 0.25 | 0.5
2023-11-22 | 0.25 | 1 | 0.25 | 0.5 | 0.75 | 1
2023-11-23 | 0.5 | 1 | 0.5 | 1 | 0 | 0
2023-11-24 | 0.25 | 0.75 | 0.5 | 0 | 0.5 | 0.5
2023-11-25 | 0 | 0.25 | 0.33 | 0.9 | 0.25 | 1
2023-11-26 | 0 | 1 | 0.75 | 1.8 | 0.5 | 0.76
2023-11-27 | 0 | 0 | 0 | 0 | 0 | 0
2023-11-28 | 0.25 | 1.5 | 1.5 | 0 | 0.25 | 0
2023-11-29 | 0 | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-30 | 0.25 | 0 | 0.33 | 0.25 | 0 | 0
2023-12-01 | 0.5 | 0.74 | 0.21 | 0 | 0.5 | 0
2023-12-02 | 0.25 | 1.5 | 1.5 | 0.5 | 0 | 1
2023-12-03 | 0 | 0 | 0 | 0 | 0 | 0
2023-12-04 | 0 | 0 | 0 | 0 | 0 | 0
2023-12-05 | 0.5 | 0 | 0 | 0.5 | 0 | 0.5
2023-12-06 | 0 | 0.66 | 0.66 | 1 | 1 | 1
2023-12-07 | 0.5 | 0 | 0.33 | 1 | 0 | 0.5
2023-12-08 | 0 | 0.33 | 0 | 0 | 0 | 0
2023-12-09 | 0 | 0 | 0 | 0 | 0 | 0
2023-12-10 | 0 | 0 | 0 | 0 | 1 | 0
2023-12-11 | 0 | 0 | 0 | 0 | 0 | 0
2023-12-12 | 0 | 0 | 0 | 0 | 0 | 0
2023-12-13 | 0 | 0 | 0 | 0 | 0 | 0
2023-12-14 | 0 | 0 | 0 | 0 | 0 | 0
2023-12-15 | 0 | 0 | 0 | 0 | 0 | 0
2023-12-16 | 0 | 0 | 0 | 0 | 0 | 0
2023-12-17 | 0 | 0 | 0 | 0 | 0 | 0
2023-12-18 | 0 | 0 | 0 | 0 | 0 | 0
2023-12-19 | 1.16 | 1.16 | 4.51 | 1.31 | 2.16 | 1.16
2023-12-20 | 1 | 0.5 | 0 | 0 | 2.5 | 0
2023-12-21 | 0 | 2.5 | 2 | 2.5 | 3 | 0
2023-12-22 | 0.5 | 3 | 3.99 | 3 | 1 | 1.5
2023-12-23 | 2 | 3 | 0 | 4 | 3 | 2
2023-12-24 | 3 | 1.75 | 0 | 2 | 2 | 2
2023-12-25 | 0 | 3 | 0 | 2 | 0 | 2
2023-12-26 | 4 | 2.75 | 0 | 2 | 0 | 3
2023-12-27 | 4 | 2 | 0 | 3 | 4 | 2
2023-12-28 | 3 | 2 | 1.08 | 1.65 | 2 | 2.5
2023-12-29 | 3 | 2 | 2.41 | 1.2 | 2 | 3
2023-12-30 | 0.5 | 1 | 0 | 1 | 0.5 | 0
2023-12-31 | 0 | 1 | 0 | 0 | 0 | 0
2024-01-01 | 0 | 1 | 0 | 0 | 0 | 0
2024-01-02 | 1.5 | 1 | 2 | 0 | 0 | 0
2024-01-03 | 2 | 1 | 1.5 | 0 | 0 | 2
2024-01-04 | 0 | 1 | 3.5 | 0 | 2 | 0
2024-01-05 | 0 | 1 | 1.5 | 0 | 0 | 0
2024-01-06 | 0 | 0 | 0 | 0 | 0 | 0
2024-01-07 | 0 | 1 | 0 | 0.88 | 2 | 0.5
2024-01-08 | 0.5 | 0.5 | 0.58 | 0 | 1 | 2
2024-01-09 | 0.5 | 0.5 | 2.16 | 0.75 | 1 | 0.5
2024-01-10 | 0 | 0 | 0 | 0 | 0 | 0
2024-01-11 | 1 | 0 | 0 | 0 | 1.15 | 1.65
2024-01-12 | 0.5 | 0 | 0 | 0 | 1 | 1.5
2024-01-13 | 0 | 0 | 0 | 0 | 0 | 0
2024-01-14 | 0 | 0 | 0 | 0 | 0 | 0
2024-01-15 | 0 | 0 | 0 | 0 | 0.5 | 0
2024-01-16 | 0.5 | 1 | 1.5 | 1 | 0.5 | 2
2024-01-17 | 0 | 0 | 6.5 | 8.5 | 0 | 0
2024-01-18 | 0 | 0 | 0 | 0 | 0 | 0

## statisticheInBudget
Pagina satistiche
id | numero ore lavoro totali | Project graphics | RAD | SDD | ODD | Implementazione | Testing | Manuali
0512115427 | 36.26 | 0 | 4.6 | 2 | 2.5 | 23.5 | 2.5 | 0
0512115910 | 50.07 | 1.75 | 8.18 | 5.49 | 1 | 29.5 | 2.99 | 0
0512106454 | 45.86 | 1 | 6.85 | 3.79 | 7.83 | 15 | 6.23 | 4
0512108680 | 50 | 1.75 | 7.66 | 3.8 | 1.5 | 21 | 7.13 | 6
0512114908 | 41.07 | 0 | 4.76 | 2.5 | 4 | 23.65 | 5 | 0
0512114332 | 41.13 | 0 | 6.32 | 4 | 3.5 | 21.65 | 4.5 | 0
ore lavoro totali
264.39

## Antonio Albanese
| Lavoratore | 0512115427 | Albanese
Data | Attività | Task | Descrizione | Ore lavoro complessive | Ore lavoro lezione lab. | Ore lavoro complessive validate | Ore lavoro lezione lab. Validate | Ore lavoro complessive validate - Ore lavoro complessive lezione lab. Validate
2023-10-16 | Meeting | C11_M1 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-10-17 | [7 empty] | 0
2023-10-18 | [7 empty] | 0
2023-10-19 | [7 empty] | 0
2023-10-20 | [7 empty] | 0
2023-10-21 | [7 empty] | 0
2023-10-22 | [7 empty] | 0
2023-10-23 | Meeting | C11_M2 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-10-24 | RAD | current system scenariosSpotahome | produzione di scenari riguardanti Spotahome | 1 | 0 | 0.34 | 0 | 0.34
2023-10-25 | [7 empty] | 0
2023-10-26 | [7 empty] | 0
2023-10-27 | [7 empty] | 0
2023-10-28 | [7 empty] | 0
2023-10-29 | [7 empty] | 0
2023-10-30 | Meeting | C11_M3 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-10-31 | [7 empty] | 0
2023-11-01 | RAD | Scenarios | Produzione scenari SC1.3 e 1.1 | 0.5 | 0 | 0.5 | 0 | 0.5
2023-11-02 | RAD | current system activity diagram Spotahome | Produzione AD Spotahome | 0.25 | 0 | 0.17 | 0 | 0.17
2023-11-03 | [7 empty] | 0
2023-11-04 | [7 empty] | 0
2023-11-05 | [7 empty] | 0
2023-11-06 | Meeting | C11_M4 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-11-07 | RAD | Use cases | Produzione Use case UC_1.3 | 1 | 0 | 1 | 0 | 1
2023-11-08 | RAD | Define functional requirments | Scrittura requisiti RF_1.1 RF_1.2 RF_1.3 RF_1.4 | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-09 | RAD | Define non-functional requirments | Scrittura RNF_5 | 0.09 | 0 | 0.09 | 0 | 0.09
2023-11-10 | RAD | Activity Diagrams | AD Annuncio Affitto | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-11 | RAD | User story | US_6 | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-12 | [7 empty] | 0
2023-11-13 | Meeting | C11_M5 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-11-14 | RAD | Navigational Path | Scrittura navigational path user page NP_2 | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-15 | RAD | Mockups | Scrittura Mockup1.0 | 0.5 | 0 | 0.5 | 0 | 0.5
2023-11-16 | RAD | Entity Boundary e Control | Scrittura entity Boundary e Controll dello scenario 1.3 | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-17 | RAD | Writing RAD | Prima stesura del RAD | 0.5 | 0 | 0.5 | 0 | 0.5
2023-11-18 | [7 empty] | 0
2023-11-19 | [7 empty] | 0
2023-11-20 | Meeting | C11_M6 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-11-21 | [7 empty] | 0
2023-11-22 | RAD | Sequence diagram | SD_3 Annuncio | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-23 | SDD | Define ER schema | Define ER scheme | 0.5 | 0 | 0.5 | 0 | 0.5
2023-11-24 | SDD | Design goals | Define design goals | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-25 | [7 empty] | 0
2023-11-26 | [7 empty] | 0
2023-11-27 | Meeting | C11_M7 | Meeting | 1.5 | 0 | 1.5 | 1.5 | 0
2023-11-28 | SDD | writing SDD | writing SDD | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-29 | [7 empty] | 0
2023-11-30 | SDD | Define project architecture | HW/SW mapping | 0.25 | 0 | 0.25 | 0 | 0.25
2023-12-01 | SDD | Define logic data model | Logic_model | 0.5 | 0 | 0.5 | 0 | 0.5
2023-12-02 | SDD | Define software control flow type | Writing the Global control and flows | 0.25 | 0 | 0.25 | 0 | 0.25
2023-12-03 | [7 empty] | 0
2023-12-04 | Meeting | C11_M8 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-12-05 | Testing | TP_7 | Writing TP_7 | 0.5 | 0 | 0.5 | 0 | 0.5
2023-12-06 | [7 empty] | 0
2023-12-07 | Testing | TCP_7 | Writing TCP_7 | 0.5 | 0 | 0.5 | 0 | 0.5
2023-12-08 | [7 empty] | 0
2023-12-09 | [7 empty] | 0
2023-12-10 | [7 empty] | 0
2023-12-11 | Meeting | C11_M9 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-12-12 | [7 empty] | 0
2023-12-13 | [7 empty] | 0
2023-12-14 | [7 empty] | 0
2023-12-15 | [7 empty] | 0
2023-12-16 | [7 empty] | 0
2023-12-17 | [7 empty] | 0
2023-12-18 | [7 empty] | 0
2023-12-19 | Meeting | C11_M10 | Meeting | 1.16 | 0 | 1.16 | 0 | 1.16
2023-12-20 | ODD | Define Class Attributes and signatures | scrittura Class_Interface_Segnalazione | 1 | 0 | 1 | 0 | 1
2023-12-21 | [7 empty] | 0
2023-12-22 | ODD | Define object design goals | Definizione degli object design goals | 0.5 | 0 | 0.5 | 0 | 0.5
2023-12-23 | Implementation | developing front end | developing-front end | 2 | 0 | 2 | 0 | 2
2023-12-24 | Implementation | developing front end | developing-front end | 3 | 0 | 3 | 0 | 3
2023-12-25 | [7 empty] | 0
2023-12-26 | Implementation | developing back-end | developing-back end | 4 | 0 | 4 | 0 | 4
2023-12-27 | Implementation | developing front end | developing-front end | 3.5 | 0 | 3.5 | 0 | 3.5
2023-12-27 | ODD | writing ODD | Writing ODD | 0.5 | 0 | 0.5 | 0 | 0.5
2023-12-28 | Implementation | developing front end | developing-front end | 3 | 0 | 3 | 0 | 3
2023-12-29 | Implementation | developing front end | dveloping front-end | 1.5 | 0 | 1.5 | 0 | 1.5
2023-12-29 | Implementation | developing back-end | dveloping back-end | 1.5 | 0 | 1.5 | 0 | 1.5
2023-12-30 | ODD | ODD review | ODD review | 0.5 | 0 | 0.5 | 0 | 0.5
2023-12-31 | [7 empty] | 0
2024-01-01 | [7 empty] | 0
2024-01-02 | Implementation | developing front end | developing-front end | 1.5 | 0 | 1.5 | 0 | 1.5
2024-01-03 | Implementation | Developing Back end | Developing back end | 2 | 0 | 2 | 0 | 2
2024-01-04 | [7 empty] | 0
2024-01-05 | [7 empty] | 0
2024-01-06 | [7 empty] | 0
2024-01-07 | [7 empty] | 0
2024-01-08 | Testing | Writing unit test plan document | Writing alloggioDAO tp | 0.5 | 0 | 0.5 | 0 | 0.5
2024-01-09 | Testing | Writing unit test case specification document | Writing alloggioDAO tcs | 0.5 | 0 | 0.5 | 0 | 0.5
2024-01-10 | [7 empty] | 0
2024-01-11 | Implementation | develop system testing | develop system testing | 1 | 0 | 1 | 0 | 1
2024-01-12 | Implementation | develop unit testing | develop unit testing | 0.5 | 0 | 0.5 | 0 | 0.5
2024-01-13 | [7 empty] | 0
2024-01-14 | [7 empty] | 0
2024-01-15 | [7 empty] | 0
2024-01-16 | Testing | Writing test incident report | writing report table | 0.5 | 0 | 0.5 | 0 | 0.5
2024-01-17 | [7 empty] | 0
2024-01-18 | [7 empty] | 0

## Francesco Pio Contaldo
| Lavoratore | 0512115910 | Contaldo
Data | Attività | Task | Descrizione | Ore lavoro complessive | Ore lavoro lezione lab. | Ore lavoro complessive validate | Ore lavoro lezione lab. Validate | Ore lavoro complessive validate - Ore lavoro complessive lezione lab. Validate
2023-10-16 | Meeting | C11_M1 | Kick-off meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-10-17 | [7 empty] | 0
2023-10-18 | Project Graphic | Logo | creazione logo UniRentHub | 0.5 | 0 | 0.5 | 0 | 0.5
2023-10-19 | Project Graphic | Palette | creazione palette colori | 0.5 | 0 | 0.5 | 0 | 0.5
2023-10-20 | [7 empty] | 0
2023-10-21 | [7 empty] | 0
2023-10-22 | [7 empty] | 0
2023-10-23 | Meeting | C11_M2 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-10-24 | Project Graphic | Logo | final fix logo | 0.5 | 0 | 0.5 | 0 | 0.5
2023-10-25 | Project Graphic | Palette | final fix palette | 0.5 | 0 | 0.25 | 0 | 0.25
2023-10-26 | RAD | Current System Scenarios Facebook | SC affitto casa + SC pubblicazione annuncio | 0.5 | 0 | 0.34 | 0 | 0.34
2023-10-27 | [7 empty] | 0
2023-10-28 | [7 empty] | 0
2023-10-29 | [7 empty] | 0
2023-10-30 | Meeting | C11_M3 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-10-31 | RAD | Scenarios | URH -> (SC 5_1 & SC 5_2) | 1 | 0 | 1 | 0 | 1
2023-11-01 | [7 empty] | 0
2023-11-02 | RAD | Current System AD | AD Facebook Affitto Casa | 1 | 0 | 0.17 | 0 | 0.17
2023-11-03 | [7 empty] | 0
2023-11-04 | [7 empty] | 0
2023-11-05 | [7 empty] | 0
2023-11-06 | Meeting | C11_M4 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-11-07 | RAD | Activity Diagrams | AD Annuncio Affitto | 0.5 | 0 | 0.5 | 0 | 0.5
2023-11-08 | RAD | UseCases | UC_5 Recensione | 0.5 | 0 | 0.5 | 0 | 0.5
2023-11-09 | [7 empty] | 0
2023-11-10 | RAD | Define functional requirements | scrittura RF_1.8, RF_2.9, RF_3.1, RF_3.2 | 0.5 | 0 | 0.5 | 0 | 0.5
2023-11-11 | RAD | Define non-functional requirements | scrittura RNF_3 | 0.5 | 0 | 0.5 | 0 | 0.5
2023-11-12 | RAD | Define User Story | Definizione US_2.0 relativo al "Login" | 0.17 | 0 | 0.17 | 0 | 0.17
2023-11-13 | Meeting | C11_M5 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-11-14 | RAD | Navigational Path | NP_5 Recensione | 0.15 | 0 | 0.15 | 0 | 0.15
2023-11-15 | RAD | Mockups | Mockup_5 Login | 0.1 | 0 | 0.1 | 0 | 0.1
2023-11-16 | RAD | Define Boundary, Control and Entity Objects | Aggiunta di Entity, Boundary e Control alla tabella comune | 0.5 | 0 | 0.5 | 0 | 0.5
2023-11-17 | RAD | Writing Rad | Prima stesura RAD | 0.5 | 0 | 0.5 | 0 | 0.5
2023-11-18 | [7 empty] | 0
2023-11-19 | RAD | Writing Rad | Writing Rad | 0.5 | 0 | 0.5 | 0 | 0.5
2023-11-20 | Meeting | C11_M6 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-11-21 | SDD | Define design goals | definizione design goals DG_3, DG_4 | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-22 | SDD | Define ER Schema | Entita relazione Schema ER | 1 | 0 | 1 | 0 | 1
2023-11-23 | SDD | Define ER Schema | Concept e rappresentazione ER | 1 | 0 | 1 | 0 | 1
2023-11-24 | SDD | Define ER Schema | Concept e rappresentazione ER | 1 | 0 | 0.75 | 0 | 0.75
2023-11-25 | RAD | Sequence diagram | SD_Prenotazione_Visita_Alloggio | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-26 | RAD | Class Diagram | Implementazione Class diagram | 1 | 0 | 1 | 0 | 1
2023-11-27 | Meeting | C11_M7 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-11-28 | RAD | Rad review | Rad review | 1.5 | 0 | 1.5 | 0 | 1.5
2023-11-29 | SDD | Boundary Condition | UCBC_4 | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-30 | [7 empty] | 0
2023-12-01 | SDD | Define System Access Control | Definizione degli accessi al sistema | 0.33 | 0 | 0.33 | 0 | 0.33
2023-12-01 | SDD | Writing SDD | scrittura del SDD | 0.41 | 0 | 0.41 | 0 | 0.41
2023-12-02 | SDD | Define Access Control Matrix | Definizione della matrice degli accessi | 1.5 | 0 | 1.5 | 0 | 1.5
2023-12-03 | [7 empty] | 0
2023-12-04 | Meeting | C11_M8 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-12-05 | [7 empty] | 0
2023-12-06 | Testing | Writing System Test Plan Document | Definizione di TP_Recensione | 0.66 | 0 | 0.66 | 0 | 0.66
2023-12-07 | [7 empty] | 0
2023-12-08 | Testing | Writing System Test Case Specification Document | Definizione TCS_Recensione | 0.33 | 0 | 0.33 | 0 | 0.33
2023-12-09 | [7 empty] | 0
2023-12-10 | [7 empty] | 0
2023-12-11 | Meeting | C11_M9 | meeting per testing e presentazione progetto | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-12-12 | [7 empty] | 0
2023-12-13 | [7 empty] | 0
2023-12-14 | [7 empty] | 0
2023-12-15 | [7 empty] | 0
2023-12-16 | [7 empty] | 0
2023-12-17 | [7 empty] | 0
2023-12-18 | [7 empty] | 0
2023-12-19 | Meeting | C11_M10 | Meeting | 1.16 | 0 | 1.16 | 0 | 1.16
2023-12-20 | ODD | Define Class attributes and signatures | Scrittura Class Interface Recensione | 0.5 | 0 | 0.5 | 0 | 0.5
2023-12-21 | Implementation | Build Database | Build Database | 2.5 | 0 | 2.5 | 0 | 2.5
2023-12-22 | ODD | Define object design goals | Definizione degli object design goals | 0.5 | 0 | 0.5 | 0 | 0.5
2023-12-22 | Implementation | Build Database | Build Database | 2.5 | 0 | 2.5 | 0 | 2.5
2023-12-23 | Implementation | Developing Back-end | Developing Back-end | 3 | 0 | 3 | 0 | 3
2023-12-24 | Implementation | Developing Back-end | Developing Back-end | 1.75 | 0 | 1.75 | 0 | 1.75
2023-12-25 | Implementation | Developing Back-end | Developing Back-end | 1 | 0 | 1 | 0 | 1
2023-12-25 | Implementation | Developing Front-end | Developing Front-end | 2 | 0 | 2 | 0 | 2
2023-12-26 | Implementation | Developing Front-end | Developing Front-end | 1 | 0 | 1 | 0 | 1
2023-12-26 | Implementation | Developing Back-end | Developing Back-end | 1.75 | 0 | 1.75 | 0 | 1.75
2023-12-27 | Implementation | Developing Back-end | Developing Back-end | 2 | 0 | 2 | 0 | 2
2023-12-28 | Implementation | Developing Back-end | Developing Back-end | 2 | 0 | 2 | 0 | 2
2023-12-29 | Implementation | Developing Back-end | Developing Back-end | 2 | 0 | 2 | 0 | 2
2023-12-30 | Implementation | Developing Back-end | Developing Back-end | 1 | 0 | 1 | 0 | 1
2023-12-31 | Implementation | Developing Back-end | Developing Back-end | 1 | 0 | 1 | 0 | 1
2024-01-01 | Implementation | Developing Back-end | Developing Back-end | 1 | 0 | 1 | 0 | 1
2024-01-02 | Implementation | Developing Back-end | Developing Back-end | 1 | 0 | 1 | 0 | 1
2024-01-03 | Implementation | Developing Back-end | Developing Back-end | 1 | 0 | 1 | 0 | 1
2024-01-04 | Implementation | Developing Back-end | Developing Back-end | 1 | 0 | 1 | 0 | 1
2024-01-05 | Implementation | Developing Back-end | Developing Back-end | 1 | 0 | 1 | 0 | 1
2024-01-06 | [7 empty] | 0
2024-01-07 | Implementation | Developing Back-end | Developing Back-end | 1 | 0 | 1 | 0 | 1
2024-01-08 | Testing | Writing Unit Test Plan Document | scrittura di TP_ClienteDAO | 0.5 | 0 | 0.5 | 0 | 0.5
2024-01-09 | Testing | Writing Unit Test Case Specification Document | scrittura TCS_ClienteDAO | 0.5 | 0 | 0.5 | 0 | 0.5
2024-01-10 | [7 empty] | 0
2024-01-11 | [7 empty] | 0
2024-01-12 | [7 empty] | 0
2024-01-13 | [7 empty] | 0
2024-01-14 | [7 empty] | 0
2024-01-15 | [7 empty] | 0
2024-01-16 | Testing | Writing Test Incident Report | Test Incident Report | 0.5 | 0 | 0.5 | 0 | 0.5
2024-01-16 | Testing | Writing Test Summary Report | Test Summary Report | 0.5 | 0 | 0.5 | 0 | 0.5
2024-01-17 | [7 empty] | 0
2024-01-18 | [7 empty] | 0

## Cristyan Esposito
| Lavoratore | 0512106454 | Esposito
Giorno | Attività | Task | Descrizione | Ore lavoro complessive | Ore lavoro lezione lab. | Ore lavoro complessive validate | Ore lavoro lezione lab. Validate | Ore lavoro complessive validate - Ore lavoro complessive lezione lab. Validate
2023-10-16 | Meeting | C11_M1 | Kick-off meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-10-17 | [7 empty] | 0
2023-10-18 | Project Graphic | Logo | creazione logo UniRentHub | 0.5 | 0 | 0.5 | 0 | 0.5
2023-10-19 | [7 empty] | 0
2023-10-20 | Project Graphic | Palette | creazione palette colori | 0.5 | 0 | 0.5 | 0 | 0.5
2023-10-21 | [7 empty] | 0
2023-10-22 | [7 empty] | 0
2023-10-23 | [7 empty] | 0
2023-10-24 | [7 empty] | 0
2023-10-25 | RAD | Current system scenarios | scrittura SC_2.1 Scenario Annuncio affitto su Spotahome | 0.5 | 0 | 0.34 | 0 | 0.34
2023-10-26 | [7 empty] | 0
2023-10-27 | [7 empty] | 0
2023-10-28 | [7 empty] | 0
2023-10-29 | [7 empty] | 0
2023-10-30 | Meeting | C11_M3 | meeting per scenari e activity diagram | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-10-31 | [7 empty] | 0
2023-11-01 | [7 empty] | 0
2023-11-02 | [7 empty] | 0
2023-11-03 | [7 empty] | 0
2023-11-04 | [7 empty] | 0
2023-11-05 | RAD | Current system activity diagram | creazione activity diagram annuncio proprietario su spotahome | 0.17 | 0 | 0.17 | 0 | 0.17
2023-11-06 | Meeting | C11_M4 | meeting per use case e requirement elicitation | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-11-07 | [7 empty] | 0
2023-11-08 | RAD | Scenarios | scrittura SC_2.1 Scenario prenotazione visita, scrittura SC_2.2 Scenario ricerca alloggio | 0.75 | 0 | 0.75 | 0 | 0.75
2023-11-09 | RAD | Activity diagrams | creazione activity diagram annuncio proprietario URH | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-10 | RAD | Use cases | scrittura UC_1 Use case Prenotazione visita alloggio | 0.5 | 0 | 0.5 | 0 | 0.5
2023-11-10 | RAD | Use cases | creazione UCD_Utente registrato | 0.17 | 0 | 0.17 | 0 | 0.17
2023-11-11 | RAD | Define functional requirements | scrittura RF_1.6, RF_1.7. RF_2.6, RF_2.7, RF_2.8, RF_6.0 | 0.24 | 0 | 0.24 | 0 | 0.24
2023-11-11 | RAD | Define Actors | Definizione degli attori del sistema | 0.17 | 0 | 0.17 | 0 | 0.17
2023-11-12 | RAD | Define non-functional requirements | scrittura RNF_4 | 0.24 | 0 | 0.24 | 0 | 0.24
2023-11-12 | RAD | Define User Story | Definizione US_3.1 relativo al RF 3.1 "Creazione Annuncio" | 0.17 | 0 | 0.17 | 0 | 0.17
2023-11-13 | Meeting | C11_M5 | meeting per requirement elicitation e requirements analysis | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-11-14 | RAD | Writing RAD | scrittura del RAD | 0.34 | 0 | 0.34 | 0 | 0.34
2023-11-14 | RAD | Use cases | creazione UCD_Utente_Locatore | 0.17 | 0 | 0.17 | 0 | 0.17
2023-11-15 | [7 empty] | 0
2023-11-16 | RAD | Navigational Path | creazione NP_ricerca_alloggio | 0.17 | 0 | 0.17 | 0 | 0.17
2023-11-17 | RAD | Mockups | riproduzione Mock-up Pagina alloggio | 0.17 | 0 | 0.17 | 0 | 0.17
2023-11-18 | RAD | Define boundary, entity, control objects | Aggiunta degli oggetti Entità, Boundary e Control nella tabella da UC_1 e da SC_2.3 | 0.17 | 0 | 0.17 | 0 | 0.17
2023-11-19 | RAD | Writing RAD | scrittura del RAD | 0.5 | 0 | 0.5 | 0 | 0.5
2023-11-20 | Meeting | C11_M6 | meeting per requirement analysis e system design | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-11-21 | RAD | Writing RAD | scrittura del RAD | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-22 | RAD | Sequence diagram | SD_Prenotazione_Visita_Alloggio | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-23 | SDD | Define Scheme ER | Definizione schema ER | 0.5 | 0 | 0.5 | 0 | 0.5
2023-11-24 | SDD | Define design goals | definizione design goals DG_9, DG_10, DG_11 | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-24 | SDD | Define subsystems | Definizione dei sottosistemi della piattaforma UniRentHub | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-25 | SDD | Writing SDD | scrittura del SDD | 0.33 | 0 | 0.33 | 0 | 0.33
2023-11-26 | SDD | Define project layers | Definizione del layer dei sottosistemi | 0.42 | 0 | 0.42 | 0 | 0.42
2023-11-26 | RAD | Define Class Diagram | Definizione del class diagram | 0.33 | 0 | 0.33 | 0 | 0.33
2023-11-27 | Meeting | C11_M7 | meeting per system design e revisione RAD | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-11-28 | RAD | RAD review | Revisione del RAD | 1.5 | 0 | 1.5 | 0 | 1.5
2023-11-29 | [7 empty] | 0
2023-11-30 | SDD | Define System Access Control | Definizione degli accessi al sistema | 0.33 | 0 | 0.33 | 0 | 0.33
2023-12-01 | SDD | Writing SDD | scrittura del SDD | 0.41 | 0 | 0.21 | 0 | 0.21
2023-12-02 | SDD | Define Access Control Matrix | Definizione della matrice degli accessi | 1.5 | 0 | 1.5 | 0 | 1.5
2023-12-03 | [7 empty] | 0
2023-12-04 | Meeting | C11_M8 | meeting per system design e testing | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-12-05 | [7 empty] | 0
2023-12-06 | Testing | Writing System Test Plan Document | Definizione di TP_Prenotazione visita | 0.66 | 0 | 0.66 | 0 | 0.66
2023-12-07 | Testing | Writing System Test Case Specification Document | Definizione TCS_Prenotazione Visita | 0.33 | 0 | 0.33 | 0 | 0.33
2023-12-08 | [7 empty] | 0
2023-12-09 | [7 empty] | 0
2023-12-10 | [7 empty] | 0
2023-12-11 | Meeting | C11_M9 | meeting per testing e presentazione progetto | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-12-12 | [7 empty] | 0
2023-12-13 | [7 empty] | 0
2023-12-14 | [7 empty] | 0
2023-12-15 | [7 empty] | 0
2023-12-16 | [7 empty] | 0
2023-12-17 | [7 empty] | 0
2023-12-18 | [7 empty] | 0
2023-12-19 | Meeting | C11_M10 | meeting per fase di implementazione e object design | 1.16 | 0 | 1.16 | 0 | 1.16
2023-12-19 | ODD | Define Project Packages | definizione dei package del sistema | 1.25 | 0 | 1.25 | 0 | 1.25
2023-12-19 | ODD | Define Class Attributes and signatures | scrittura Class_Interface_Cliente | 2 | 0 | 2 | 0 | 2
2023-12-19 | ODD | Writing ODD | scrittura del ODD | 0.1 | 0 | 0.1 | 0 | 0.1
2023-12-20 | [7 empty] | 0
2023-12-21 | Implementation | Build database | build and fix del db | 2 | 0 | 2 | 0 | 2
2023-12-22 | Implementation | Build database | Fix ed insert dati | 3 | 0 | 3 | 0 | 3
2023-12-22 | ODD | Define object design goals | Definizione degli object design goals | 0.83 | 0 | 0.83 | 0 | 0.83
2023-12-22 | ODD | Writing ODD | scrittura del ODD | 0.16 | 0 | 0.16 | 0 | 0.16
2023-12-23 | [7 empty] | 0
2023-12-24 | [7 empty] | 0
2023-12-25 | [7 empty] | 0
2023-12-26 | [7 empty] | 0
2023-12-27 | [7 empty] | 0
2023-12-28 | ODD | Define Project Packages | Correzione package del sistema | 0.75 | 0 | 0.75 | 0 | 0.75
2023-12-28 | ODD | Writing ODD | scrittura del ODD | 0.33 | 0 | 0.33 | 0 | 0.33
2023-12-29 | ODD | Define Design Patterns | Scrittura design patterns | 2 | 0 | 2 | 0 | 2
2023-12-29 | ODD | Writing ODD | scrittura del ODD | 0.41 | 0 | 0.41 | 0 | 0.41
2023-12-30 | [7 empty] | 0
2023-12-31 | [7 empty] | 0
2024-01-01 | [7 empty] | 0
2024-01-02 | Implementation | Developing front-end | Developing front-end | 1 | 0 | 1 | 0 | 1
2024-01-02 | Implementation | Developing back-end | Developing back-end | 1 | 0 | 1 | 0 | 1
2024-01-03 | Implementation | Developing front-end | Developing front-end | 1.5 | 0 | 1.5 | 0 | 1.5
2024-01-04 | Implementation | Developing back-end | Developing back-end | 2 | 0 | 2 | 0 | 2
2024-01-04 | Implementation | Developing front-end | Developing front-end | 1.5 | 0 | 1.5 | 0 | 1.5
2024-01-05 | Implementation | Developing back-end | Developing back-end | 1.5 | 0 | 1.5 | 0 | 1.5
2024-01-06 | [7 empty] | 0
2024-01-07 | [7 empty] | 0
2024-01-08 | Testing | Writing Unit Test Plan Document | scrittura di TP_ClienteDAO | 0.58 | 0 | 0.58 | 0 | 0.58
2024-01-09 | Testing | Writing Unit Test Case Specification Document | scrittura TCS_ClienteDAO | 0.66 | 0 | 0.66 | 0 | 0.66
2024-01-09 | Implementation | Developing front-end | Developing front-end | 1.5 | 0 | 1.5 | 0 | 1.5
2024-01-10 | [7 empty] | 0
2024-01-11 | [7 empty] | 0
2024-01-12 | [7 empty] | 0
2024-01-13 | [7 empty] | 0
2024-01-14 | [7 empty] | 0
2024-01-15 | [7 empty] | 0
2024-01-16 | Testing | Writing Test Incident Report | scrittura del TIR | 0.5 | 0 | 0.5 | 0 | 0.5
2024-01-16 | Testing | Writing Test Summary Report | scrittura del TSR | 1 | 0 | 1 | 0 | 1
2024-01-17 | Testing | Review Test Documents | Review Test Documents | 2.5 | 0 | 2.5 | 0 | 2.5
2024-01-17 | Manual | Writing User Manual | scrittura del MU | 2.5 | 0 | 2.5 | 0 | 2.5
2024-01-17 | Manual | Writing Installation Guide | scrittura del MDI | 1.5 | 0 | 1.5 | 0 | 1.5
2024-01-18 | [7 empty] | 0

## Iliano Fasolino
| Lavoratore | 0512108680 | Fasolino
Giorno | Attività | Task | Descrizione | Ore lavoro Complessive | Ore lavoro lezione lab. | Ore lavoro complessive validate | Ore lavoro lezione lab. Validate | Ore lavoro complessive validate - Ore lavoro complessive lezione lab. Validate
2023-10-16 | Meeting | C11_M1 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-10-17 | [7 empty] | 0
2023-10-18 | Project Graphic | Logo | creazione logo UniRentHub | 0.5 | 0 | 0.5 | 0 | 0.5
2023-10-19 | Project Graphic | Palette | creazione palette colori | 0.5 | 0 | 0.5 | 0 | 0.5
2023-10-20 | [7 empty] | 0
2023-10-21 | [7 empty] | 0
2023-10-22 | [7 empty] | 0
2023-10-23 | Meeting | C11_M2 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-10-24 | Project Graphic | Logo | final fix logo | 0.5 | 0 | 0.5 | 0 | 0.5
2023-10-25 | Project Graphic | Palette | final fix palette | 0.5 | 0 | 0.25 | 0 | 0.25
2023-10-26 | RAD | Current System Scenarios | SC Utente Interessato + SC Annuncio Affitto + various fixes | 1 | 0 | 0.34 | 0 | 0.34
2023-10-27 | [7 empty] | 0
2023-10-28 | [7 empty] | 0
2023-10-29 | [7 empty] | 0
2023-10-30 | Meeting | C11_M3 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-10-31 | RAD | Scenarios | URH -> (SC 6_1 & SC 6_2) | 1 | 0 | 1 | 0 | 1
2023-11-01 | RAD | Current System Activity Diagrams | AD Spotahome UserSide + various AD fixes | 0.25 | 0 | 0.17 | 0 | 0.17
2023-11-02 | [7 empty] | 0
2023-11-03 | [7 empty] | 0
2023-11-04 | [7 empty] | 0
2023-11-05 | [7 empty] | 0
2023-11-06 | Meeting | C11_M4 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-11-07 | RAD | Activity Diagrams | AD Annuncio Proprietario + various fixes | 0.5 | 0 | 0.5 | 0 | 0.5
2023-11-08 | RAD | UseCases | UC_2 Annuncio studente | 0.5 | 0 | 0.5 | 0 | 0.5
2023-11-08 | RAD | UseCases | UCD_3 Admin | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-09 | RAD | Define functional requirements | Scrittura RF_1.10, RF_2.4, RF_2.5, RF_6.2 | 0.5 | 0 | 0.5 | 0 | 0.5
2023-11-10 | RAD | Define non-functional requirements | Scrittura RNF_6 | 0.5 | 0 | 0.5 | 0 | 0.5
2023-11-11 | RAD | Define User Story | US_1.0 | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-12 | RAD | Define Actors | Define Actors | 0.1 | 0 | 0.1 | 0 | 0.1
2023-11-13 | Meeting | C11_M5 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-11-14 | RAD | Navigational Path | NP_4 Acquisto Casa | 0.15 | 0 | 0.15 | 0 | 0.15
2023-11-15 | RAD | Mockups | Mockup_1 Homepage | 0.1 | 0 | 0.1 | 0 | 0.1
2023-11-16 | RAD | Define Boundary, Control and Entity Objects | Aggiunta di Entity, Boundary e Control alla tabella comune | 0.5 | 0 | 0.5 | 0 | 0.5
2023-11-17 | [7 empty] | 0
2023-11-18 | RAD | Writing Rad | Writing Rad | 0.5 | 0 | 0.5 | 0 | 0.5
2023-11-19 | RAD | Navigational Path | NP_4 Acquisto Casa final fix | 0.15 | 0 | 0.15 | 0 | 0.15
2023-11-20 | Meeting | C11_M6 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-11-21 | RAD | Writing Rad | Writing Rad | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-22 | SDD | Define Design Goals | Tabella Design Goals + DG_5, DG_6 | 1 | 0 | 0.5 | 0 | 0.5
2023-11-23 | SDD | Define ER Schema | Concept e rappresentazione ER | 1 | 0 | 1 | 0 | 1
2023-11-24 | [7 empty] | 0
2023-11-25 | RAD | Sequence Diagram | SD_2 Affitto Studente | 0.75 | 0 | 0.75 | 0 | 0.75
2023-11-25 | RAD | Writing Rad | Writing Rad | 0.15 | 0 | 0.15 | 0 | 0.15
2023-11-26 | RAD | Class Diagram | Implementazione Class diagram | 1 | 0 | 1 | 0 | 1
2023-11-26 | SDD | Define Persitence Entity | Definizione delle entità del progetto | 0.5 | 0 | 0.5 | 0 | 0.5
2023-11-26 | SDD | Writing SDD | Writing SDD | 0.5 | 0 | 0.3 | 0 | 0.3
2023-11-27 | Meeting | C11_M7 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-11-28 | [7 empty] | 0
2023-11-29 | SDD | Boundary Condition | UCBC_2 | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-30 | SDD | Writing SDD | Writing SDD | 0.25 | 0 | 0.25 | 0 | 0.25
2023-12-01 | [7 empty] | 0
2023-12-02 | SDD | Define How to Protect Sensitive Data | Writing Define How to Protect Sensitive Data | 0.5 | 0 | 0.5 | 0 | 0.5
2023-12-03 | [7 empty] | 0
2023-12-04 | Meeting | C11_M8 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-12-05 | SDD | SDD Review | SDD Review | 0.5 | 0 | 0.5 | 0 | 0.5
2023-12-06 | Testing | Test Plan | Writing Test Plan Annuncio | 1 | 0 | 1 | 0 | 1
2023-12-07 | Testing | Test Case Specification | Writing Test Case Specification Annuncio | 1 | 0 | 1 | 0 | 1
2023-12-08 | [7 empty] | 0
2023-12-09 | [7 empty] | 0
2023-12-10 | [7 empty] | 0
2023-12-11 | Meeting | C11_M9 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-12-12 | [7 empty] | 0
2023-12-13 | [7 empty] | 0
2023-12-14 | [7 empty] | 0
2023-12-15 | [7 empty] | 0
2023-12-16 | [7 empty] | 0
2023-12-17 | [7 empty] | 0
2023-12-18 | [7 empty] | 0
2023-12-19 | Meeting | C11_M10 | Meeting | 1.16 | 0 | 1.16 | 0 | 1.16
2023-12-19 | ODD | Writing ODD | Writing ODD | 0.15 | 0 | 0.15 | 0 | 0.15
2023-12-20 | [7 empty] | 0
2023-12-21 | Implementation | Build Database | Build Database | 2.5 | 0 | 2.5 | 0 | 2.5
2023-12-22 | ODD | Define object design goals | Definizione degli object design goals | 0.5 | 0 | 0.5 | 0 | 0.5
2023-12-22 | Implementation | Build Database | Build Database | 2.5 | 0 | 2.5 | 0 | 2.5
2023-12-23 | ODD | Define Class Attributes Signatures | Scrittura Class Interface Dipendente | 0.5 | 0 | 0.5 | 0 | 0.5
2023-12-23 | Implementation | Developing Front-end | Developing Front-end | 1.5 | 0 | 1.5 | 0 | 1.5
2023-12-23 | Implementation | Developing Back-end | Developing Back-end | 2 | 0 | 2 | 0 | 2
2023-12-24 | Implementation | Developing Back-end | Developing Back-end | 2 | 0 | 2 | 0 | 2
2023-12-25 | Implementation | Developing Front-end | Developing Front-end | 2 | 0 | 2 | 0 | 2
2023-12-26 | Implementation | Developing Back-end | Developing Back-end | 0.5 | 0 | 0.5 | 0 | 0.5
2023-12-26 | Implementation | Developing Front-end | Developing Front-end | 1.5 | 0 | 1.5 | 0 | 1.5
2023-12-27 | Implementation | Developing Front-end | Developing Front-end | 3 | 0 | 3 | 0 | 3
2023-12-28 | ODD | Writing ODD | Writing ODD | 0.15 | 0 | 0.15 | 0 | 0.15
2023-12-28 | Implementation | Developing Front-end | Developing Front-end | 1.5 | 0 | 1.5 | 0 | 1.5
2023-12-29 | ODD | Writing ODD | Writing ODD | 0.2 | 0 | 0.2 | 0 | 0.2
2023-12-29 | Implementation | Developing Front-end | Developing Front-end | 1 | 0 | 1 | 0 | 1
2023-12-30 | Implementation | Developing Front-end | Developing Front-end | 1 | 0 | 1 | 0 | 1
2023-12-31 | [7 empty] | 0
2024-01-01 | [7 empty] | 0
2024-01-02 | [7 empty] | 0
2024-01-03 | [7 empty] | 0
2024-01-04 | [7 empty] | 0
2024-01-05 | [7 empty] | 0
2024-01-06 | [7 empty] | 0
2024-01-07 | Testing | Writing Unit Test Plan Document | Test Plan PostDAO | 0.88 | 0 | 0.88 | 0 | 0.88
2024-01-08 | [7 empty] | 0
2024-01-09 | Testing | Writing Unit Test Case Specification Document | Test Case Specification PostDAO | 0.75 | 0 | 0.75 | 0 | 0.75
2024-01-10 | [7 empty] | 0
2024-01-11 | [7 empty] | 0
2024-01-12 | [7 empty] | 0
2024-01-13 | [7 empty] | 0
2024-01-14 | [7 empty] | 0
2024-01-15 | [7 empty] | 0
2024-01-16 | Testing | Writing Test Incident Report | Test Incident Report | 0.5 | 0 | 0.5 | 0 | 0.5
2024-01-16 | Testing | Writing Test Summary Report | Test Summary Report | 0.5 | 0 | 0.5 | 0 | 0.5
2024-01-17 | Testing | Review Test Documents | Review Test Documents | 2.5 | 0 | 2.5 | 0 | 2.5
2024-01-17 | Manual | Writing User Manual | User Manual | 3.5 | 0 | 3.5 | 0 | 3.5
2024-01-17 | Manual | Writing Installation Guide | Installation Guide | 2.5 | 0 | 2.5 | 0 | 2.5
2024-01-18 | [7 empty] | 0

## Marco Greco
| Lavoratore | 0512114908 | Greco
Giorno | Attività | Task | Descrizione | Ore lavoro complessive | Ore lavoro lezione lab. | Ore lavoro complessive validate | Ore lavoro lezione lab. Validate | Ore lavoro complessive validate - Ore lavoro complessive lezione lab. Validate
2023-10-16 | Meeting | C11_M1 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-10-17 | [7 empty] | 0
2023-10-18 | [7 empty] | 0
2023-10-19 | [7 empty] | 0
2023-10-20 | [7 empty] | 0
2023-10-21 | [7 empty] | 0
2023-10-22 | [7 empty] | 0
2023-10-23 | Meeting | C11_M2 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-10-24 | RAD | current system scenarios Facebook | produzione di scenari riguardanti lcoatore mette annuncio | 1 | 0 | 0.34 | 0 | 0.34
2023-10-25 | [7 empty] | 0
2023-10-26 | [7 empty] | 0
2023-10-27 | [7 empty] | 0
2023-10-28 | [7 empty] | 0
2023-10-29 | [7 empty] | 0
2023-10-30 | Meeting | C11_M3 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-10-31 | [7 empty] | 0
2023-11-01 | RAD | Scenarios | produzione scenari SC_2.0 e SC_3.1 | 0.5 | 0 | 0.5 | 0 | 0.5
2023-11-02 | RAD | current system activity diagrams | produzione AD Facebook degli scenari | 0.25 | 0 | 0.17 | 0 | 0.17
2023-11-03 | [7 empty] | 0
2023-11-04 | [7 empty] | 0
2023-11-05 | [7 empty] | 0
2023-11-06 | Meeting | C11_M4 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-11-07 | RAD | Use cases | produzione UC UC_3.1 | 1 | 0 | 1 | 0 | 1
2023-11-07 | RAD | Use cases | UCD_4 Homechecker | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-08 | RAD | define functional requirements | scrittura requisiti RF_2.0/2.1/3.0/1.4/1.9/1.10 | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-09 | RAD | define non-functional requirements | scrittura RNF_1 | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-10 | RAD | User story | Scrittura User Story US_4.0 | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-11 | [7 empty] | 0
2023-11-12 | [7 empty] | 0
2023-11-13 | Meeting | C11_M5 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-11-14 | RAD | statechart diagram | scrittura statechart diagram alloggio | 0.5 | 0 | 0.5 | 0 | 0.5
2023-11-15 | RAD | Navigational path | scrittura navigational path NP_4.0 | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-16 | RAD | Mockups | Scrittura mockup3.0 | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-17 | [7 empty] | 0
2023-11-18 | RAD | Entity Boundary e Control | scrittura entity boundary e control degli scenari SC_2.0/3.0 e di UC_3.1 | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-19 | RAD | Writing RAD | Prima stesura RAD | 0.5 | 0 | 0.5 | 0 | 0.5
2023-11-20 | Meeting | C11_M6 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-11-21 | SDD | Define design goal | Definizione dei design goal DG_9 DG_10 | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-22 | SDD | Define ER schema | Definizione dello schema ER | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-23 | [7 empty] | 0
2023-11-24 | SDD | Define persistence entity | Definizione delle persistence entity | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-24 | SDD | Define subsystem | Definizione dei sottosistemi del progetto | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-25 | SDD | Sequence Diagram | SD_3 Annuncio | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-26 | SDD | Define project layers | definizione dei layer di progetto | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-26 | SDD | Writing SDD | scrittura dell'SDD | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-27 | Meeting | C11_M7 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-11-28 | SDD | Boundary Conditions | Definzione delle boundary condition UCBC_1 | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-29 | [7 empty] | 0
2023-11-30 | [7 empty] | 0
2023-12-01 | SDD | Define project architecture | Definizione del mapping Hardware e software | 0.5 | 0 | 0.5 | 0 | 0.5
2023-12-02 | [7 empty] | 0
2023-12-03 | [7 empty] | 0
2023-12-04 | Meeting | C11_M8 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-12-05 | [7 empty] | 0
2023-12-06 | Testing | Writing System Test Plan Document | Scrittura Test Plan TC_8 | 1 | 0 | 1 | 0 | 1
2023-12-07 | [7 empty] | 0
2023-12-08 | [7 empty] | 0
2023-12-09 | [7 empty] | 0
2023-12-10 | Testing | Writing System Test Case Specification Plan Document | Scrittura TCS_8 | 1 | 0 | 1 | 0 | 1
2023-12-11 | Meeting | C11_M9 | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-12-12 | [7 empty] | 0
2023-12-13 | [7 empty] | 0
2023-12-14 | [7 empty] | 0
2023-12-15 | [7 empty] | 0
2023-12-16 | [7 empty] | 0
2023-12-17 | [7 empty] | 0
2023-12-18 | [7 empty] | 0
2023-12-19 | Meeting | C11_M11 | Meeting | 1.16 | 0 | 1.16 | 0 | 1.16
2023-12-19 | ODD | Define Class Attributes Signatures | Scrittura Class_interface_Affitto | 1 | 0 | 1 | 0 | 1
2023-12-20 | Implementation | Developing Back-end | Developing Back-end | 2 | 0 | 2 | 0 | 2
2023-12-20 | Implementation | Developing Front-end | Developing Front-end | 0.5 | 0 | 0.5 | 0 | 0.5
2023-12-21 | Implementation | Developing Back-end | Developing Back-end | 2 | 0 | 2 | 0 | 2
2023-12-21 | Implementation | Developing Front-end | Developing Front-end | 1 | 0 | 1 | 0 | 1
2023-11-22 | ODD | Define Object Design Goals | Definizione degli object design goals | 0.5 | 0 | 0.5 | 0 | 0.5
2023-12-22 | Implementation | Developing Back-end | Developing Back-end | 0.5 | 0 | 0.5 | 0 | 0.5
2023-12-22 | Implementation | Developing Front-end | Developing Front-end | 0.5 | 0 | 0.5 | 0 | 0.5
2023-12-23 | Implementation | Developing Back-end | Developing Back-end | 2 | 0 | 2 | 0 | 2
2023-12-23 | Implementation | Developing Front-end | Developing Front-end | 1 | 0 | 1 | 0 | 1
2023-12-24 | Implementation | Developing Back-end | Developing Back-end | 1 | 0 | 1 | 0 | 1
2023-12-24 | Implementation | Developing Front-end | Developing Front-end | 1 | 0 | 1 | 0 | 1
2023-12-25 | [7 empty] | 0
2023-12-26 | [7 empty] | 0
2023-12-27 | Implementation | Developing Back-end | Developing Back-end | 4 | 0 | 4 | 0 | 4
2023-12-28 | Implementation | Developing Back-end | Developing Back-end | 2 | 0 | 2 | 0 | 2
2023-12-29 | ODD | Define desing Patterns | Scrittura design patterns | 2 | 0 | 2 | 0 | 2
2023-12-30 | ODD | ODD review | ODD review | 0.5 | 0 | 0.5 | 0 | 0.5
2023-12-31 | [7 empty] | 0
2024-01-01 | [7 empty] | 0
2024-01-02 | [7 empty] | 0
2024-01-03 | [7 empty] | 0
2024-01-04 | Implementation | Developing Back end | Developing Back-end | 2 | 0 | 2 | 0 | 2
2024-01-05 | [7 empty] | 0
2024-01-06 | [7 empty] | 0
2024-01-07 | Implementation | Developing Back end | fix bug e aggiunta alert | 2 | 0 | 2 | 0 | 2
2024-01-08 | Testing | Writing Unit Test Plan Document | scrittura di TP_AffittoDAO | 1 | 0 | 1 | 0 | 1
2024-01-09 | Testing | Writing Unit Test Case Specification Document | scrittura di TCS_AffittoDAO | 1 | 0 | 1 | 0 | 1
2024-01-10 | [7 empty] | 0
2024-01-11 | Implementation | Developing unit tests | Sviluppo test di Unità | 1.15 | 0 | 1.15 | 0 | 1.15
2024-01-12 | Implementation | Developing system tests | Sviluppo test di Sistema | 1 | 0 | 1 | 0 | 1
2024-01-13 | [7 empty] | 0
2024-01-14 | [7 empty] | 0
2024-01-15 | Testing | Execute tests | Esecuzione test di Unità | 0.5 | 0 | 0.5 | 0 | 0.5
2024-01-16 | Testing | Execute tests | Esecuzione test di Sistema | 0.5 | 0 | 0.5 | 0 | 0.5
2024-01-17 | [7 empty] | 0
2024-01-18 | [7 empty] | 0

## Giuseppe Pio Sorrentino
| Lavoratore | 0512114332 | Sorrentino
Giorno | Attività | Task | Descrizione | Ore lavoro complessive | Ore lavoro lezione lab. | Ore lavoro complessive validate | Ore lavoro lezione lab. Validate | Ore lavoro complessive validate - Ore lavoro complessive lezione lab. Validate
2023-10-16 | Meeting | C11_M1 Kick-off meeting | Meeting | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-10-17 | [7 empty] | 0
2023-10-18 | [7 empty] | 0
2023-10-19 | [7 empty] | 0
2023-10-20 | [7 empty] | 0
2023-10-21 | [7 empty] | 0
2023-10-22 | [7 empty] | 0
2023-10-23 | Meeting | C11_M2 | Meeting n°2 | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-10-24 | RAD | Current System Scenarios Facebook | SC affitto casa + SC pubblicazione annuncio | 0.5 | 0 | 0.34 | 0 | 0.34
2023-10-25 | [7 empty] | 0
2023-10-26 | [7 empty] | 0
2023-10-27 | [7 empty] | 0
2023-10-28 | [7 empty] | 0
2023-10-29 | [7 empty] | 0
2023-10-30 | Meeting | C11_M3 | Meeting n°3 | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-10-31 | [7 empty] | 0
2023-11-01 | RAD | Scenarios URH | SC_1.1 + SC_1.2 | 1 | 0 | 1 | 0 | 1
2023-11-02 | RAD | Current System AD | AD Facebook Affitto Casa | 1 | 0 | 0.17 | 0 | 0.17
2023-11-03 | [7 empty] | 0
2023-11-04 | [7 empty] | 0
2023-11-05 | [7 empty] | 0
2023-11-06 | Meeting | C11_M4 | Meeting n°4 | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-11-07 | RAD | UseCases | UC_6 Caricazione Annuncio | 1 | 0 | 1 | 0 | 1
2023-11-07 | RAD | UseCases | UCD6_Studente | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-08 | RAD | Define functional requirements | Scrittura requisiti RF_1.0, RF_2.2, RF_2.3, RF_6.1 | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-09 | RAD | Define non-functional requirements | Scirttura requisiti RNF_2 | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-10 | RAD | User Story | US_5 Prenotazione Visita | 0.15 | 0 | 0.15 | 0 | 0.15
2023-11-11 | [7 empty] | 0
2023-11-12 | [7 empty] | 0
2023-11-13 | Meeting | C11_M5 | Meeting n°5 | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-11-14 | RAD | Define Dynamic Model | Statechart Diagram | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-15 | RAD | Define Dynamic Model | NP_3 Caricazione Annuncio | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-16 | RAD | Define Dynamic Model | MockUp_6 Risultati Ricerca | 0.15 | 0 | 0.15 | 0 | 0.15
2023-11-17 | RAD | Define Buondary, control and entity | Aggiunta di Buondary, control e entity alla tabella comune | 0.5 | 0 | 0.5 | 0 | 0.5
2023-11-18 | RAD | Writing Rad | Writing RAD | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-19 | [7 empty] | 0
2023-11-20 | Meeting | C11_M6 | Meeting n°6 | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-11-21 | SDD | Define Desing goal | Tabella Desing goal | 1 | 0 | 0.5 | 0 | 0.5
2023-11-22 | SDD | Define ER schema | Concept e rappresentazione ER | 1 | 0 | 1 | 0 | 1
2023-11-22 | [7 empty] | 0
2023-11-24 | SDD | Define Persitence Entity | Definizione delle entità del progetto | 0.5 | 0 | 0.5 | 0 | 0.5
2023-11-25 | SDD | Define subsystem | Definizione dei sottosistemi del progetto | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-25 | RAD | Sequence Diagram | SD_2 Affitto Studente | 0.75 | 0 | 0.75 | 0 | 0.75
2023-11-26 | RAD | Writing rad | writing rad | 1 | 0 | 0.76 | 0 | 0.76
2023-11-27 | Meeting | C11_M7 | Meeting n°7 | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-11-28 | [7 empty] | 0
2023-11-29 | SDD | Boundry Condition | UCBC_3 | 0.25 | 0 | 0.25 | 0 | 0.25
2023-11-30 | [7 empty] | 0
2023-12-01 | [7 empty] | 0
2023-12-02 | SDD | Define How to protect sensitive data | Writing Define How to protect sensitive data | 0.5 | 0 | 0.5 | 0 | 0.5
2023-12-02 | SDD | Define Logic Data Model | Definizione del modello logico | 0.5 | 0 | 0.5 | 0 | 0.5
2023-12-03 | [7 empty] | 0
2023-12-04 | Meeting | C11_M8 | Meeting n°8 | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-12-05 | SDD | Revisione SDD | Revisione SDD | 0.5 | 0 | 0.5 | 0 | 0.5
2023-12-06 | Testing | Test Plan | Test Plan pubblicazione annuncio | 1 | 0 | 1 | 0 | 1
2023-12-07 | Testing | Test Case Specification | Test Case Specification Pubblicazione annuncio | 0.5 | 0 | 0.5 | 0 | 0.5
2023-12-08 | [7 empty] | 0
2023-12-09 | [7 empty] | 0
2023-12-10 | [7 empty] | 0
2023-12-11 | Meeting | C11_M9 | Meeting n°9 | 1.5 | 1.5 | 1.5 | 1.5 | 0
2023-12-12 | [7 empty] | 0
2023-12-13 | [7 empty] | 0
2023-12-14 | [7 empty] | 0
2023-12-15 | [7 empty] | 0
2023-12-16 | [7 empty] | 0
2023-12-17 | [7 empty] | 0
2023-12-18 | [7 empty] | 0
2023-12-19 | Meeting | c11_M10 | Meeting n°10 | 1.16 | 0 | 1.16 | 0 | 1.16
2023-12-20 | [7 empty] | 0
2023-12-21 | [7 empty] | 0
2023-12-22 | ODD | Define Object Design Goals | Definizione degli ocject design goals | 0.5 | 0 | 0.5 | 0 | 0.5
2023-12-22 | ODD | Define Class Attributes and signature | Class interface Alloggio | 1 | 0 | 1 | 0 | 1
2023-12-23 | ODD | Define Trade Off | Define Trade Off | 2 | 0 | 2 | 0 | 2
2023-12-24 | Implementation | Developing Front end | Developing Front end | 2 | 0 | 2 | 0 | 2
2023-12-25 | Implementation | Developing Front end | Developing Front end | 2 | 0 | 2 | 0 | 2
2023-12-26 | Implementation | Developing Front end | Developing Front end | 3 | 0 | 3 | 0 | 3
2023-12-27 | Implementation | Developing Back end | Developing back end | 2 | 0 | 2 | 0 | 2
2023-12-28 | Implementation | Developing Back end | Developing Back end | 2 | 0 | 2 | 0 | 2
2023-12-28 | Implementation | Developing Front end | Developing Front end | 0.5 | 0 | 0.5 | 0 | 0.5
2023-12-29 | Implementation | Developing Back end | Developing Back end | 2 | 0 | 2 | 0 | 2
2023-12-29 | Implementation | Developing Front end | Developing Front end | 1 | 0 | 1 | 0 | 1
2023-12-30 | [7 empty] | 0
2023-12-31 | [7 empty] | 0
2024-01-01 | [7 empty] | 0
2024-01-02 | [7 empty] | 0
2024-01-03 | Implementation | Developing Back end | Developing Back end | 2 | 0 | 2 | 0 | 2
2024-01-04 | [7 empty] | 0
2024-01-05 | [7 empty] | 0
2024-01-06 | [7 empty] | 0
2024-01-07 | Testing | Writing unit test plan document | Scrittura test plan DipendeneDAO | 0.5 | 0 | 0.5 | 0 | 0.5
2024-01-07 | [7 empty] | 0
2024-01-08 | Implementation | Developing Back end | fix bug del sito e aggiunta alert | 2 | 0 | 2 | 0 | 2
2024-01-09 | Testing | Writing unit test case specification document | Scrittura test case specification DipendeneDAO | 0.5 | 0 | 0.5 | 0 | 0.5
2024-01-10 | [7 empty] | 0
2024-01-11 | Implementation | Developing Unit Test | Developing unit test | 1.65 | 0 | 1.65 | 0 | 1.65
2024-01-12 | Implementation | Developing System test | Developing system test | 1.5 | 0 | 1.5 | 0 | 1.5
2024-01-13 | [7 empty] | 0
2024-01-14 | [7 empty] | 0
2024-01-15 | [7 empty] | 0
2024-01-16 | Testing | Execute tests | Execute Test | 2 | 0 | 2 | 0 | 2
2024-01-17 | [7 empty] | 0
2024-01-18 | [7 empty] | 0